## 0.
STANDARDS FROM THE
CONSTRUCTION INDUSTRY
Remarks on Terms read on Standards Sheets
.
Labourer | Workers contributing in performing activities, earlier distinguished mainly due to standard rates (payments) purposes - such as: unskilled workers, trained workers, dikers, concrete labourers - all abbreviated as "lab"
Carpenter | Referring to workers of trades such as carpentry works and scaffolding
Material | Numerical data of material needs are for informing (demonstrative) purposes only, and shouldn't be used directly for any delivery or procurement purposes. They serve as numerical aids for managerial considerations such as transport and on-site storage.
Product | Referring (mentioning) main and/or significant materials and structural elements, not including materials of less amount needed or of less significance - such as pins, cramps, wires, dry colours, etc.
Concrete mixtures | Constituents of them are collected in Appendices - by ranges of technical features and of components
and mortars

## 1. pre works
Clear-felling, plantation and gardening works
Nr. | Activity | Unit | Time-standard | Skill | Item number | prices
|  |  | (hour) |  |  | material price | fee | machinery cost
1. | Felling, power saw, trunk diameter10-50 cm | pcs | 0.7 | labourer | 0.001 | 0 | 15.3014 | 2.4192
2. | Felling, power saw, trunk diameter above 51 cm | pcs | 0.94 | labourer | 0.002 | 0 | 42.1344 | 5.7792
3. | Goubbing, ditch refilling, equipped, trunk diameter 10-50 cm | pcs | 0.95 | labourer | 0.003 | 0 | 260.568 | 18.1306
4. | Goubbing, ditch refilling, equipped, trunk diameter above 51 cm | pcs | 1.8 | labourer | 0.004 | 0 | 86.1538 | 18.3053
5. | Brush cutting, manually, trunk diameter below 10 cm | 10m2 | 1.15 | labourer | 0.005 | 0 | 35.0381 | 0
6. | Grassing, flat or slope area, manually | 10m2 | 0.4 | labourer | 0.006 | 0 | 13.3056 | 0
7. | Grass cutting, mower, below 4 cm | 10m2 | 0.52 | labourer | 0.007 | 0 | 2.2176 | 4.1496

## 2. earthworks
Earthworks
Nr. | Activity | Unit | Soil consistency |  |  |  | Skill | Item number | prices
|  |  | I-II. | III. | IV. | V.
|  |  | Time-standard (hour) | [5 empty] | material price | fee | machinery cost
1. | Topsoil excavation, depth less than 10 cm, | m3 | 0.79 | 1.2 | - | - | labourer | 0.008 | 0 | 0 | 1.885
(and for each 10 cms on)
2. | Excavation, from trench without timbering, depth less than 1,5 m | m3 | 1.17 | 1.71 | 2.76 | 3.98 | labourer | 0.009 | 0 | 6.9854 | 1.9152
vertical or sloped earthwall
3. | Excavation, from ditch without timbering | m3 | 1.46 | 2.49 | 3.76 | 4.64 | labourer | 0.010 | 0 | 0.33264 | 3.7699
4. | Excavation, from trench with timbered vertical earthwall | m3 | 1.47 | 2.67 | 4.07 | 4.79 | labourer | 0.011 | 8.232 | 3.528 | 0
5. | Excavation, from ditch with timbered vertical earthwall | m3 | 1.46 | 2.66 | 4.08 | 4.87 | labourer | 0.012 | 11.76 | 5.04 | 0
6. | Refill and spread in trench | m3 | 0.61 | 0.85 | 1.08 | - | labourer | 0.013 | 12.4656 | 5.3424 | 0
7. | Refinery earthwork after rough excavation by equipment, depth 10-20 cm | 10m2 | 2.16 | 3.81 | 5.58 | - | labourer | 0.014 | 0 | 0.11088 | 1.0483
8. | Levelling the ground, without compacting, depth below 10 cm | 10m2 | 0.50 | 0.72 | 0.97 | - | labourer | 0.015 | 0 | 0 | 0.38304
9. | Levelling the ground, without compacting, depth 10-20 cm | 10m2 | 0.96 | 1.35 | 1.81 | - | labourer | 0.016 | 0 | 2.5502 | 6.263
10. | Sloping in a hollow or on embankment, mean thickness 10 cm | 10m2 | 0.72 | 1.02 | 1.43 | - | labourer | 0.017 | 0.0016464 | 0.33264 | 1.7035
11. | Sloping in a hollow or on embankment, mean thickness 10-15 cm | 10m2 | 0.92 | 1.32 | 2.02 | - | labourer | 0.018 | 0 | 0.5544 | 2.1
12. | Subgrading, excavated earth deposited, depth below 10 cm | 10m2 | 1.11 | 1.54 | 2.03 | - | labourer | 0.019 | 0 | 0 | 0.38304
(and for each 10 cms on)
13. | Loading earth or building rubbish to truck, | m3 | 0.73 | 0.92 | 1.08 | 1.27 | labourer | 0.020 | 0 | 0 | 0.89712
or moving it within an arm reach distance
14. | Spreading earth or building rubbish, mean depth below 20 cm, | m3 | 0.17 | 0.25 | 0.33 | - | labourer | 0.021 | 0 | 0 | 1.885
after rough spreading by equipment

## 3. timbering, metal
Timbering, metal sheetwalls |  |  | Timbering, metal
Nr. | Activity | Unit | Live-labour |  |  |  | Material |  |  | Item number | prices
|  |  | Building | Removing | Relocating | Skill | Uses |  | Product
|  |  | Time-standard (hour) |  |  |  | First built | Rebuilt |  |  | material price | fee | machinery cost
1. | Trench timbering | m2 | 0.05 | 0.04 | 0.08 | carpenter | 0.09 m3 | 0.0045 m3 | plank | 0.022 | 0.81984 | 14.6362 | 0
| both sides |  | 0.25 | 0.08 | 0.31 | labourer | 0.01 m3 | 0.0005 m3 | log
close horizontal planking
s.c.: I-IV
2. | Trench timbering | m2 | 0.05 | 0.03 | 0.07 | carpenter | 0.056 m3 | 0.0028 m3 | plank | 0.023 | 0.50064 | 11.975 | 0
| both sides |  | 0.25 | 0.06 | 0.32 | labourer | 0.01 m3 | 0.0005 m3 | log
open horizontal planking
s.c.: III-IV
3. | Trench timbering | m2 | 0.08 | 0.06 | 0.12 | carpenter | 0.058 m3 | 0.003 m3 | plank | 0.024 | 0.84 | 18.517 | 0
| both sides |  | 0.33 | 0.12 | 0.42 | labourer | 0.037 m3 | 0.0019 m3 | lumber
| close vertical planking | [5 empty] | 0.018 m3 | 0.0009 m3 | log
s.c.: I-IV
4. | Trench timbering | m2 | 0.05 | 0.04 | 0.08 | carpenter | 0.03 m3 | 0.0015 m3 | plank | 0.025 | 0.59472 | 13.6382 | 0
| both sides |  | 0.2 | 0.12 | 0.3 | labourer | 0.037 m3 | 0.0019 m3 | lumber
| open vertical planking | [5 empty] | 0.018 m3 | 0.0009 m3 | log
s.c.: III-IV
5. | Ditch timbering | m2 | 0.18 | 0.11 | - | carpenter | 0.06 m3 | 0.003 m3 | plank | 0.026 | 1.1995 | 13.9709 | 0
| single side |  | 0.53 | 0.22 |  | labourer | 0.058 m3 | 0.0029 m3 | lumber
| close horizontal planking | [5 empty] | 0.07 m3 | 0.0035 m3 | log
s.c.: I-IV
with stays or anchoring
6. | Ditch timbering | m2 | 0.18 | 0.09 | - | carpenter | 0.037 m3 | 0.0019 m3 | plank | 0.027 | 1.0046 | 10.4227 | 0
| single side |  | 0.50 | 0.18 |  | labourer | 0.058 m3 | 0.0029 m3 | lumber
| open horizontal planking | [5 empty] | 0.07 m3 | 0.0035 m3 | log
s.c.: III-IV
with stays or anchoring
7. | Ditch timbering | m2 | 0.33 | 0.26 | - | carpenter | 0.059 m3 | 0.003 m3 | plank | 0.028 | 1.2062 | 15.6341 | 0
| single side |  | 0.88 | 0.52 |  | labourer | 0.046 m3 | 0.0023 m3 | lumber
| close vertical planking | [5 empty] | 0.053 m3 | 0.0027 m3 | log
s.c.: I-IV
with stays or anchoring
8. | Ditch timbering | m2 | 0.26 | 0.11 | - | carpenter | 0.031 m3 | 0.0015 m3 | plank | 0.029 | 0.92064 | 12.6403 | 0
| single side |  | 0.69 | 0.22 |  | labourer | 0.046 m3 | 0.0023 m3 | lumber
| open vertical planking | [5 empty] | 0.053 m3 | 0.0027 m3 | log
s.c.: III-IV
with stays or anchoring
9. | Pit (well) timbering | m2 | 0.2 | 0.05 | - | carpenter | 0.071 m3 | 0.0036 m3 | plank | 0.030 | 0.81648 | 18.6278 | 0
| (four sides) |  | 0.35 | 0.15 |  | labourer | 0.04 m3 | 0.002 m3 | lumber
[7 empty] | 0.02 m3 | 0.001 m3 | log
10. | Metal pile-plank | m2 | 0.34 | 0.29 | - | carpenter | 1.24 m2 | 0.04 m2 | steel plank | 0.031 | 61.488 | 295.9387 | 101.6064
| poling-board timbering |  | 0.80 | 0.58 |  | labourer | 0.034 m3 | 0.0034 m3 | lumber
| both sides | [5 empty] | 0.012 m3 | 0.0012 m3 | log
vertical plank coverage
s.c.: I-IV
removal by pulleyblock
11. | Sheetwall piling, | m2 | 8 men/equip | 8 men/equip | - | smith | 1.06 m2 | 0.150 m2 | steel plank. | 0.032 | 51.8112 | 29.9376 | 16.3901
| average soil conditions |  | 5 m2/hour | 10 m2/hour |  | labourer | 0.022 m3 | 0.0022 m3 | lumber

## 4. drain, backfill
Drainage, filtration layer and backfill construction
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time-standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Drain-pipe laying, on bedding, in trench | lm | 0.16 | labourer | 3.1 pcs | terracotta pipe or | 0.033 | 17.173 | 2.2176 | 0
[5 empty] | or 2.04 pcs | enamelled clay-tube
2. | Collector and drain-system laying | m | 0.16 | labourer | 1.015 m | concrete pipe | 0.034 | 8.5243 | 4.3243 | 0
| on bedding, in trench, attached |  |  |  |  | (cement duct)
| (diameter 10-15-20 cm) |  |  |  |  | tube with base
or socket
3. | Bedding bottom-drain or bottom-channel | m3 | 2.09 | labourer | 1.23 m3 | screened gravel | 0.035 | 8.111 | 35.0381 | 0
4. | Covering bottom-drain or bottom-channel | m | 0.07 | labourer | 5 pcs | partition brick | 0.036 | 3.9245 | 5.7658 | 0
5. | Building stratified filter (drain) mass | m3 | 2.57 | labourer | 1.08 m3 | screened gravel | 0.037 | 26.1778 | 24.948 | 0
(or sand, or riprap)
6. | Sealing drain or channel | m3 | 1.32 | labourer | 1.23 m3 | mine-clay, bitumen or cement | 0.038 | 8.2589 | 25.7242 | 0
| (barrier construction) |  |  |  |  | and soil
7. | Spreading drain-blanket (layer) | m3 | 1.83 | labourer | 1.14 m3 | gravel | 0.039 | 6.4814 | 27.3874 | 0
| on ready-made grade |  |  |  |  | (sand, grail)
8. | Building temporary drain system | m | 1.25 | labourer | 16.7 pcs | stock brick | 0.040 | 1.0248 | 0.44352 | 0
on bedding or in trench, attached
9. | Building temporary drain system | m | 0.16 | labourer | 5.4 pcs | crest tile | 0.041 | 1.4179 | 0.44352 | 0
| on bedding or in trench, attached |  |  |  | or 0.0085 m3 | of faggot
10. | Backfill construction | m3 | 0.1 | labourer | 0.3075 m3 | gravel | 0.042 | 7.1232 | 8481 | 0
maximun slope: 1:3
spread by equipment (e.g. grader)

## 5. flat foundation
Flat foundation
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time-standard | Skill | Qunatity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Blinding, thickness below 10 cm | m3 | 4.43 | labourer | 1.01 m3 | concretex | 0.049 | 42.42 | 49.4525 | 0
2. | Concreting plain concrete or RC strip foundation, | m3 | 3.19 | labourer | 1.01 m3 | concretex | 0.050 | 42.42 | 29.9376 | 7.5802
footings, slab- (mat-) or beam-grid fundation
including compacting
3. | Concreting plain concrete or RC strip foundation, | m3 | 0.7 | labourer | 1.01 m3 | concretex | 0.051 | 45.8136 | 11.088 | 3.8237
footings, slab- (mat-) or beam-grid fundation
applying concrete pump
4. | Concrete filling in sleeve foundation | m3 | 9.82 | labourer | 1.01 m3 | concretex | 0.052 | 45.8136 | 31.4899 | 7.5802
5. | Gravel fill, spreaded in layers of width 20-50 cm | m3 | 0.29 | labourer | 1.14 m3 | gravel | 0.053 | 6.8779 | 24.7262 | 0
including compacting, in grade
6. | Gravel bed spreaded in grade, | m3 | 0.17 | labourer | 1.14 m3 | gravel | 0.054 | 8.2286 | 24.7262 | 0
thinckness range 10-20 cm
7. | Recovering gravel bed | m3 | 0.5 | labourer | - | - | 0.055 | 0 | 3.3264 | 1.1962

## 6. dewatering
Dewatering
Nr. | Activity | Unit | Labour |  |  | Material |  | Item number | Prices
|  |  | Building | Removing | Skill | Quantity | Product
|  |  | Time-standard (hour) | [5 empty] | Material price | Fee | Machinery cost
1. | Laying pipes for top (open) draining | lm | 0.65 | - | labourer | 31.1 pcs | terracotta pipe | 0.043 | 49.9363 | 106.6666 | 0
| including bedding (x) |  |  |  |  | 0.12 m3 | gravel
2. | Constructing top (open) draining sump | pcs | 4.0 | 0.8 | labourer | 1.353 pcs | 80/75 shaft ring | 0.044 | 10.1002 | 5.3222 | 0
| off shaft rings, bottomed |  |  |  |  | 0.198 m3 | concrete
3. | Constructing vacuum-well | pcs | 0.5 | 0.1 | driller | 1.02 m/lm | zinc coated steel pipex | 0.045 | 6.8107 | 16.8538 | 0.88704
| not deeper than 7.5 m |  | 1.5 | 0.3 | labourer | 1 pc | perfect well
0.6-2.4 m distances, in loose soil (x)
4. | Constructing vacuum-well | pcs | 0.6 | 0.12 | driller | 1.02 m/lm | zinc coated steel pipex | 0.046 | 6.7402 | 31.9334 | 3.5482
| not deeper than 7.5 m |  | 1.8 | 0.36 | labourer | 1 pc | perfect well
0.6-2.4 m distances, in heavy soil (x)
5. | Constructing point-well | pcs | 6.5 | 1.3 | driller | 1.02 m/lm | zinc coated steel pipex | 0.047 | 51.7608 | 150.6859 | 489.3941
| not deeper than 12 m (x) |  | 19.5 | 4.0 | labourer | 1.02 m/lm | perforated casingx
| (approx. 2.0 m distances, NPS 300-400) |  |  |  |  | 1.02 m/lm | sleeve pipe NPS 200-300
6. | Fitting collector- or force-pipe for | lm | 0.3 | 0.06 | plumber | 1.02 m | NPS 100-NPS 300x | 0.048 | 1.4616 | 22.8413 | 0
| vacuum-well or point-well dewatering |  | 0.6 | 0.12 | labourer

## 7. deep foundation
Deep foundations, piles and sheetwalls(x)
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time-standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Preparing, adjusting and lowering RC piles | m | 5-6 workers/equipment | labourer | 1.015 m | RC pile | 0.056 | 97.4904 | 25.1698 | 14.7336
3 m/hour
2. | Bored RC piling | m | 4-5 workers/equipment | labourer | x | concretex | 0.057 | 9.0384 | 4.2134 | 43.092
|  |  | 0,5 m/hour |  | xxx | reinforcement
[5 empty] | 0.034 m | guide pipe
3. | SOIL-MEC bored piling | m | 6-8 workers/equipment | labourer | x | concretex | 0.058 | 89.544 | 14.6362 | 27.8981
|  |  | 4 m/hour |  | x | slurry
[5 empty] | xxx | reinforcement
[5 empty] | 1.15 m | sleeve pipe
4. | Franki-system piling | m | 5-6 workers/equipment | labourer | 0.45 m3 | concretex | 0.059 | 36.7752 | 25.835 | 29.9645
2 m/hour
5. | Sheet-wall piling | m2 | 12 workers/equipment | labourer | x | concretex | 0.060 | 56.1859 | 6.431 | 16.7429
| (excavation, slurry, reinforcement, concreting) |  | 20 m2/shift |  | xx | slurry
[5 empty] | xxx | reinforcement
6. | Chiselling-off pile cap or leader beam | m3 | 15 hours/plugger | labourer | - | - | 0.061 | 0 | 101.677 | 0
air compressor + plugger (air-hammer)

## 8. in situ concrete pre works
In-situ plain concrete and RC structures
(preliminary and posteriory works)
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time-standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Mixing concrete or mortar, | m3 | 2.22 | labourer | x |  | 0.062 | 26.413 | 1.6632 | 4.5965
drum-mixer feeded manually
2. | Mixing concrete, | m3 | 0.38 | labourer | x |  | 0.063 | 159.4992 | 63.756 | 0.08064
drum mixer and power feeder
3. | Mixing mortar, power mixer | m3 | 0.67 | labourer | x |  | 0.064 | 122.1696 | 50.4504 | 0.05376
4. | Processing reinforcing steel | t | 9.6 | steel fixer | 1.04 | reinforcing steel | 0.065 | 871.92 | 290.64 | 0
| at central steel plant |  | 4.8 | labourer
(straightening, cutting, bending)
5. | Fixing reinforcement on site | t | 14.2 | steel fixer | 1.04 | reinforcing steel | 0.066 | 712.656 | 457.9344 | 14.0717
|  |  | 7.6 | labourer
6. | Processing reinforcing steel and | 1,5*1,5 m piece | 25.6 | steel fixer | 1.04 | reinforcing steel | 0.067 | 691.1016 | 1352.736 | 12.6672
| fixing reinforcement on site |  | 12.8 | labourer
(straightening, cutting, bending, fixing)
7. | Fixing weld steel-mesh | t | 12.3 | steel fixer | 1.04 | weld settel-mesh | 0.068 | 29.3832 | 9.7944 | 0
| (manufactured) reinforcement |  | 4.1 | labourer |  | reinforcement
8. | Preparing contraction joint, power saw, | m | 0.18 | labourer | 0.02 t | rubberized asphalt | 0.069 | 0 | 5.3222 | 3.2054
bitumen joint-sealing
9. | Preparing expansion joint, power saw, | m | 0.24 | labourer | 0.02 t | rubberized asphalt | 0.070 | 1.7808 | 0.5544 | 0
| bitumen joint-sealing |  |  |  | 0.0124 t | bitumen
[5 empty] | 0.911 m2 | 120 bitumen felt

## 9. in situ concrete concreting
In-situ plain concrete and RC structures
(concreting)
Nr. | Activity | Unit | Manual | conveyor | mixer | crane + | elevator, | concrete | Skill | Material |  | Item number | Prices
|  |  |  | belt, below | truck | concrete | above | pump
|  |  |  | 6 m height |  | bucket | 6 m height
|  |  | Time-standard (hour) | [6 empty] | Quantity | Product |  | Material price | Fee | Machinery cost
1. | Concreting vertical | m3 | 5.42 | 5.19 | - | 2.83 | 4.22 | derived | lab. | 1.01 | concretex | 0.071 | 263.8944 | 113.0976 | 0
| structures (walls, piers, etc.) | [6 empty] | from
2. | Concreting slabs, | m3 | 3.84 | 5.62 | 3.0 | 3.26 | 4.65 | output | lab. | 1.01 | concretex | 0.072 | 261.7776 | 112.1904 | 0
| floor structures | [6 empty] | of pump
3. | Concreting beams, | m3 | 3.16 | 5.3 | - | 2.94 | 4.33 |  | lab. | 1.01 | concretex | 0.073 | 52.4362 | 12.4186 | 3.8237
ring-beams, stairs
and other structures
4. | Concreting subbase or | m3 | 4.43 | - | - | - | - |  | lab. | 1.01 | concretex | 0.074 | 42.42 | 40.3603 | 0
protective layer
5. | Concreting subbase or | m3 | 1.6 | [5 empty] | lab. | 1.01 | concretex | 0.075 | 183.456 | 98.784 | 0
protective layers processed,
compacted and floated by
power tools and equipment
6. | Concrete subbase layer | m3 | 5.69 | [5 empty] | lab. | 1.01 | concretex | 0.076 | 47.2954 | 51.5592 | 0
below sealing

## 10. prefabricated
Lifting and placing prefabricated
plain concrete and RC structures
Nr. | Activity | Unit | Weight of structural element (unit) | [5 empty] | Skill | Material |  | Item number | Prices
|  |  | 0.5 t | 2 t | 5 t | 10 t | 20 t | 40 t
|  |  | Time-standard (hour) | [6 empty] | Quantity | Product |  | Material price | Fee | Machinery cost
1. | Placing front panel, hung by | piece | 0.25 | 0.33 | 0.38 | - | - | - | welder | 1.01 | prefabr.struct. | 0.077 | 23.8022 | 2.3285 | 0
| crane, fixing welded or bolted | (unit) | 0.25 | 0.33 | 0.38 |  |  |  | smith |  | element (unit)
|  |  | 0.75 | 0.99 | 1.14 |  |  |  | labourer
2. | Placing (sleeve) foundation | piece | - | 0.45 | 0.58 | 0.7 | - | - | welder | 1.01 pcs | prefabr.struct. | 0.078 | 493.92 | 211.68 | 0
| block (on blinding) | (unit) |  | 0.9 | 1.26 | 1.4 |  |  | smith | 0.04 m3 | element (unit)
|  |  |  | 0.9 | 1.26 | 1.4 |  |  | labourer |  | mortarx
3. | Placing pier or column, | piece | 0.52 | 0.61 | 1.24 | 1.38 | - | - | welder | 1.01 | prefabr.struct. | 0.079 | 658.56 | 282.24 | 0
| fixing welded, no grout | (unit) | 0.52 | 0.61 | 1.24 | 1.38 |  |  | smith |  | element (unit)
|  |  | 1.56 | 1.83 | 3.72 | 4.14 |  |  | labourer
4. | Placing RC beam, lintel or | piece | 0.13 | 0.52 | 0.6 | 1.23 | 2.67 | - | welder | 1.01 | prefabr.struct. | 0.080 | 27.048 | 11.592 | 0
| joist, fixing welded, no grout | (unit) | 0.13 | 0.52 | 0.6 | 1.23 | 2.67 |  | smith |  | element (unit)
|  |  | 0.39 | 1.56 | 1.8 | 3.87 | 8.01 |  | labourer
5. | Placing floor- or roof-piece, | piece | 0.14 | 0.3 | 0.44 | 0.6 | - | - | welder | 1.01 pcs | prefabr.struct. | 0.081 | 129.4037 | 39.9168 | 0
| fixing welded, no grout | (unit) | 0.14 | 0.3 | 0.44 | 0.6 |  |  | smith | 0.012 m3 | element (unit)
|  |  | 0.42 | 0.9 | 1.32 | 1.8 |  |  | labourer |  | mortarx
6. | Placing other elements | piece | 0.33 | [5 empty] | welder | 1.01 pcs | prefabr.struct. | 0.082 | 599.8272 | 18.517 | 0
| (arms of stairs, | (unit) | 0.33 | [5 empty] | smith | 0.01 m3 | element (unit)
| moulding, balcony, attic) |  | 0.99 | [5 empty] | labourer |  | mortarx
7. | Grouting fixing joints | m3 | 9.73 | [5 empty] | labourer | 1.05 | concretex | 0.083 | 0 | 133.056 | 0

## 11. masonry labour
Masonry structures (labour)
Nr. | Activity | Unit | Masonry piece (block) | [6 empty] | Skill | Item number | Prices
|  |  | Standard. | Elevated | Double- | Masonry | Rubblestone | Partition | Concrete
|  |  | brick | brick | sized | block | (backed) | brick, thick | masonry
[5 empty] | brick | e.g. B30 |  | 6 or 10 cm | block
|  |  | Time-standard (hour) | [8 empty] | Material price | Fee | Machinery cost
1. | Pier or column | m3 | 7.68 | - | - | - | - | - | - | mason | 0.085 | 17.7542 | 14.747 | 0
|  |  | 1.4 | [6 empty] | labourer
2. | Chimney-breast | m2 | 5.49 | - | - | - | - | - | - | mason | 0.086 | 240.24 | 196.56 | 0
| (for fume) |  | 0.79 | [6 empty] | labourer
| (std. or chimney brick) | m2 | - | - | - | - | - | - | 0.46 | mason | 0.087
[9 empty] | 0.46 | labourer
3. | Air chimney | m2 | 0.78 | - | - | - | - | 0.94 | - | mason | 0.088 | 270.48 | 115.92 | 0
|  |  | 0.22 |  |  |  |  | 0.18 |  | labourer
|  | m2 | - | - | - | - | - | - | 0.44 | mason | 0.089
[9 empty] | 0.32 | labourer
4. | Protecting wall | m2 | 0.54 | - | - | - | - | - | - | mason | 0.092 | 9.5995 | 10.4227 | 0
| (at sealing, proofing) |  | 0.42 | [6 empty] | labourer
5. | Vertical loadbearing wall, with Masonry block Thickness 30 cm | m2 | 3.19 | 2.72 | 2.3 | 1.98 | 11.48 | - | - | mason | 0.084 | 33.768 | 11.256 | 0
|  |  | 3.13 | 2.92 | 2.43 | 1.98 | 4.51 |  |  | labourer
6. | Vertical loadbearing wall, with Masonry block Thickness 38cm | m2 | 3.19 | 2.72 | 2.3 | 1.98 | 11.48 | - | - | mason | 0.084 | 36.792 | 12.264 | 0
|  |  | 3.13 | 2.92 | 2.43 | 1.98 | 4.51 |  |  | labourer
7. | Vertical loadbearing wall, with Masonry block Thickness 44cm | m2 | 3.19 | 2.72 | 2.3 | 1.98 | 11.48 | - | - | mason | 0.084 | 36.792 | 12.264 | 0
|  |  | 3.13 | 2.92 | 2.43 | 1.98 | 4.51 |  |  | labourer
8. | Vertical loadbearing wall, with Concrete block Thickness 20 cm | m2 | 3.19 | 2.72 | 2.3 | 1.98 | 11.48 | - | - | mason | 0.084 | 27.72 | 22.68 | 0
|  |  | 3.13 | 2.92 | 2.43 | 1.98 | 4.51 |  |  | labourer
9. | Vertical loadbearing wall, with Concrete block Thickness 40 cm | m2 | 3.19 | 2.72 | 2.3 | 1.98 | 11.48 | - | - | mason | 0.084 | 53.7768 | 43.9992 | 0
|  |  | 3.13 | 2.92 | 2.43 | 1.98 | 4.51 |  |  | labourer
10. | Partition wall, Ceramic block Thickness 10 cm | m2 | 0.41 | - | 0.76 | 0.65 | - | 0.42 | - | mason | 0.091 | 18.816 | 8.064 | 0
|  |  | 0.15 |  | 0.27 | 0.24 |  | 0.61 |  | labourer
11. | Partition wall, with Ceramic block Thickness 12 cm | m2 | 0.41 | - | 0.76 | 0.65 | - | 0.42 | - | mason | 0.091 | 20.2272 | 8.6688 | 0
|  |  | 0.15 |  | 0.27 | 0.24 |  | 0.61 |  | labourer

## 12. masonry material (hidden)
| Masonry structures (material) | [13 empty] | kőműves szerkezetek - anyagok
Nr. | Structure | Unit | Standard | Elevated | Double | Masonry | Rubblestone | Partition | Prefabr. | Item number | Prices |  |  | Tételszám | Tételszöveg |  | EZ SZERINTEM CSAK AZ ÉPÍTŐANYAGRA VONATKOZIK ÉS ILYEN NEM KELL, VAGY TÉVEDEK?
|  |  | brick | brick | sized | block | (backed) | brick, thick | chimney
[5 empty] | brick | e.g. B30 |  | 6 or 10 cm | blocks
|  |  | Masonry pieces and mortar needs | [7 empty] | Material price | Fee | Machinery cost
1. | Vertical loadbearing wall, | m3 | 404 pcs | 309 pcs | 202 pcs | 121 pcs | 106 pcs std. bricks | - | - | 0.093 | [5 empty] | függőleges teherhordó falazataok
| filling work, spandrel |  | 0.211 m3 | 0.182 m3 | 0.149 m3 | 0.121 m3 | 1.0 m3rubblestone
0.278 m3
2. | Pier or column | m3 | 450 pcs | - | - | - | - | - | - | 0.094 | [5 empty] | oszlop vagy pillér
0.214 m3
3. | Chimney-breast | m3 | 383 pcs | - | - | - | - | - | - | 0.095
| (for fume) |  | 0.2 m3
| (std. or chimney brick) | m | - | - | - | - | - | - | 3.15 pcs | 0.096
0.007 m3
4. | Air chimney | m2 | 33 pcs | - | - | - | - | 13 pcs | - | 0.097 | [5 empty] | szellőző kémény
|  |  | 0.012 m3 |  |  |  |  | 0.007 m3
|  | m | - | - | - | - | - | - | 1.03 | 0.098
5. | Air duct | m | 16.6 pcs | - | 8.4 pcs | - | - | 2.6 pcs | - | 0.099 | [5 empty] | NEM TUOM
| (at floor structures) |  | 0.022 m3
6. | Brick-on-edge | m2 | 55 pcs | - | - | - | - | 12.7 pcs | - | 0.100 | [5 empty] | válaszfal vagy falszakaksz falalzásassa
| or partition wall |  | 0.022 m3 |  |  |  |  | 0.006 m3
7. | Protecting wall | m2 | 55 pcs | - | - | - | - | - | - | 0.101 | [5 empty] | szigetelés védő fal
| (at sealing, proofing) |  | 0.022 m3
| EZT A FÜLET NEM ÉRTEM MINEK KELL, SZERINTEM TÖRÖlHETŐ | [13 empty] | VÁZKERÁMIA FAL FALAZÁS
TÉGLAFAL FALAZÁS
ATTIKA FAL FALAZÁS?

## 13. assembly and other masonry
Assembly and other masonry works
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Building brick sewer (channel) or duct, | m | 0.49 | mason | 45 pcs | Standard brick | 0.102 | 48.8645 | 176.6318 | 6.1723
| concrete bottom, clearance 30x50 cm |  | 0.79 | labourer | 0.045 m3 | concretex
[5 empty] | 0.019 m3 | mortar for renderingx
[5 empty] | 0.007 m3 | mortar for floatingx
2. | Building brick cable-duct, | m | 0.2 | mason | 8 pcs | standard brick | 0.103 | 19.6459 | 2.772 | 1.68
| clearance 12x12 cm |  | 0.2 | labourer | 3.4 pcs | duct block
[5 empty] | 0.002 m3 | mortar for masonryx
3. | Building rabitz (mesh) channel (duct) | m2 | 2.3 | mason | 0.041 m3 | gypsum- or cement-mortar | 0.104 | 7.5902 | 54.4421 | 0
| (gypsum or cement) |  | 2.3 | labourer | 1.05 m2 | rib-wire mesh
[5 empty] | 2 kg | reinforcing steel
[5 empty] | 0.025 m3 | wood plank
4. | Concrete pavement, cast on site, | m2 | 0.35 | mason | 0.088 m3 | concretex | 0.105 | 5.077 | 8.9813 | 0
| gravel bedding, not thicker than 8 cm |  | 0.48 | labourer | 0.084 m3 | gravel
5. | Concrete pavement, precast stone flags | m2 | 0.25 | mason | 6.32 pcs | stone flag | 0.106 | 12.3614 | 6.9854 | 0
| (e.g. 40x40 cm) |  | 0.43 | labourer
6. | Concrete gutter (channel), | lm | 0.24 | mason | 0.041 m3 | concretex | 0.107 | 0 | 13.4165 | 11.5248
| on 8 cm gravel bed |  | 0.21 | labourer | 0.035 m3 | gravel
[5 empty] | 0.01 m3 | shutter board
7. | Concrete coping, not thicker than 10 cm, | m2 | 0.9 | mason | 0.092 m3 | concretex | 0.108 | 7.8859 | 39.3624 | 0
| on chimney, on fence- or fender-wall, etc. |  | 0.45 | labourer | 0.024 m3 | shutter board

## 14. water proof
Water proofing
Nr. | Activity | Unit | Any | Horizontal surface |  | Vertical surface |  | Skill | Material |  | Item number | Prices
|  |  | surface | below | above | below | above
|  |  |  | 50 m2 | 50 m2 | 50 m2 | 50 m2
|  |  | Time standard (hour) | [5 empty] | Quantity | Product |  | Material price | Fee | Machinery cost
1. | Bituminous emulsion, | m2 | 1.01 | - | - | - | - | proof worker | 0.04 t | bituminous | 0.109 | 0.36624 | 0.22176 | 0
| single coat |  | 0.77 |  |  |  |  | labourer |  | emulsion
2. | Bituminous emulsion | m2 | 2.02 | - | - | - | - | proof worker | 0.08 t | bituminous | 0.110 | 11.6726 | 6.6528 | 0
| double coat |  | 1.44 |  |  |  |  | labourer |  | emulsion
3. | Bituminous felt | m2 | - | 6.03 | 4.56 | 8.22 | 5.93 | proof worker | 115 m2 | bituminous felt | 0.111 | 2.5771 | 2.3285 | 0
| single coat |  |  | 7.58 | 5.33 | 10.16 | 7.87 | labourer | 0.3 t | bitumen
4. | Bituminous felt | m2 | - | 11.28 | 8.34 | 15.27 | 10.69 | proof worker | 230 m2 | bituminous felt | 0.112 | 4.153 | 5.9875 | 0
| double coat |  |  | 12.83 | 9.89 | 17.21 | 12.63 | labourer | 0.44 t | bitumen
5. | Bituminous felt | m2 | - | 16.7 | 11.58 | 21.87 | 16.0 | proof worker | 345 m2 | bituminous felt | 0.113 | 17.2738 | 10.9771 | 0
| triple coat |  |  | 18.2 | 13.4 | 23.81 | 17.94 | labourer | 0.6 t | bitumen
6. | Bituminous felt | m2 | - | 21.87 | 15.54 | 30.73 | 19.61 | proof worker | 460 m2 | bituminous felt | 0.114 | 20.9765 | 11.975 | 0
| four coats |  |  | 23.49 | 17.09 | 32.67 | 21.55 | labourer | 0.76 t | bitumen
7. | Plastic/rubber | 100m2 | 4.5 | - | - | - | - | proof worker | 115 m2 | insulating foil. | 0.115 | 5.6549 | 2.4394 | 0
| felt/foil, single |  | 3.1 |  |  |  |  | labourer | 115 m | binding tape

## 15. heat and noise ins
Heat- and noise insulation
Nr. | Activity | Unit | Horizontal | Vertical | Skill | Material |  | Item number | Prices
|  |  | surface | surface
|  |  | Time standard (hour) |  |  | Quantity | Product |  | Material price | Fee | Machinery cost
1. | Porour brick tile insulation | m2 | 0.16 | 0.33 | mason | 13 pcs | porous brick tile | 0.116 | 4.9896 | 3.3264 | 0
| embedded in mortar |  | 0.16 | 0.33 | labourer | 0.02 m3 | mortarx
2. | Perlite-concrete insulation, | m3 | 5.2 | 11.5 | mason | 1.01 m3 | perlite-concretex | 0.117 | 176.4672 | 45.239 | 0
| thickness below 4 cm |  | 5.2 | 3.5 | labourer
3. | Perlite-concrete insulation, | m3 | 2.8 | 6.3 | mason | 1.01 m3 | perlite-concretex | 0.118 | 155.5277 | 45.239 | 0
| thickness above 4 cm |  | 5.6 | 3.5 | labourer
4. | Gas-silicate tile insulation, | m2 | 0.16 | 0.23 | mason | 8.1 pcs | gas-silicate tile | 0.119 | 19.6291 | 7.7616 | 0
| tile size 52.8x24 cm |  | 0.16 | 0.23 | labourer | 0.02 m3 | mortarx
5. | Gas-silicate insulation, | m2 | 0.09 | 0.2 | mason | 5.4 pcs | gas-silicate tile | 0.120 | 53.639 | 10.5336 | 0
| tile size 79.5x24 cm |  | 0.09 | 0.2 | labourer | 0.02 m3 | mortarx
6. | Foamed plastic heat-insulation, | m2 | - | 0.75 | insulator | 2.06 m2 | insulating board | 0.121 | 28.3651 | 4.7678 | 0
| two layers, bonded |  |  | 0.5 | labourer | 1.2 kg | adhesive (bond)
7. | Glassfiber mat heat-insulation, | m2 | 0.44 | 0.44 | insulator | 1.07 m2 | glassfiber mat | 0.122 | 25.5595 | 4.7678 | 0
| hard crusted |  | 0.44 | 0.44 | labourer | 7.7 kg | fossil meal
[6 empty] | 7.3 kg | gypsum
8. | Heat- and noise insulation, | m2 | 0.22 | 0.18 | mason | 1.03 m2 | insulating board | 0.123 | 38.3107 | 5.3222 | 0
| insulating board, |  | 0.22 | 0.18 | labourer
nailed, on roof or on wall

## 16. roof structures
Roof structures and roofings
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Roof trussing (standing and fixing) | floor | 0.68 | carpenter | 0.006 m3 | lagging strip | 0.124 | 5.5642 | 11.6424 | 0
| (woodwork: 0,03 m3/floor m2) | m2 | 0.34 | labourer | 0.0232 m3 | timber
[5 empty] | 0.0026 m3 | shutter board
2. | Roof lathing or planking, | floor | 0.22 | carpenter | 0.0053 m3 | rib (for tiles) | 0.125 | 1.7203 | 3.8808 | 0
| for below tiles or slates | m2 | 0.11 | labourer | or 0.0074 m3 | rib (for slates)
[5 empty] | or 0.0253 m3 | plank (for slates)
3. | Slating on laths or on planks | m2 | 20.1 | roof tiler | 85 pcs | rim (flash) plate | 0.126 | 46.5696 | 14.9688 | 0
| (quantities for standard slate of 40x40 cm) |  | 2.1 | labourer | 1000 pcs | asbestos slate
[5 empty] | 39 pcs | bonnet piece
4. | Corrugated asbestos sheet, 1/2 period | m2 | 15.58 | roof tiler | 46 pcs | 250x100 cm Cas | 0.127 | 8.4806 | 3.8808 | 0
| overlapping, on wood or on concrete |  | 8.01 | labourer | or 75 pcs | 160x110 cm Cas
5. | Corrugated polyester sheet 1/1 period | m2 | 12.0 | roof tiler | 78.8 pcs | 206x80 cm Cps | 0.128 | 11.6827 | 5.3222 | 0
| overlapping |  | 12.0 | labourer
6. | Tile roofing, standard tiles | m2 | 8.2 | roof tiler | 1800 pcs | wire-cut gutter tile | 0.129 | 11.8373 | 3.659 | 0
|  |  | 9.8 | labourer | 1600 pcs | pressed gutter tile
7. | Adhesive-bonded roofing on concrete or | m2 | 4.49 | insulator | 113 m2 | sanded bitum. felt | 0.130 | 0 | 4.4352 | 0
| on heat-insulating surface, single layer |  | 5.38 | labourer | 0.22 t | bitumen
8. | Adhesive-bonded roofing on concrete or | m2 | 8.12 | insulator | 226 m2 | sanded bitum.felt | 0.131 | 6.888 | 3.3264 | 0
| on heat-insulating surface, double layer |  | 9.74 | labourer | 0.38 t | bitumen
9. | Heat-insulation and wapour-barrier, | m2 | 89.0 | insulator | 115 m2 | NEOACID sheet | 0.132 | 0.85008 | 0.88704 | 0
| combined of NEOACID sheet and |  | 80.0 | labourer. | 208 pcs | expanded cork sheet
| of 3-6 cm thick expanded cork sheet |  |  |  | 115 m2 | sanded bitum. felt
[5 empty] | 0.81 t | bitumen
10. | Metal-sheet roofing, single seamed sheets | m2 | 39.0 | insulator | 122 m2 | sheet-metal | 0.133 | 43.139 | 8.2051 | 0
|  |  | 36.0 | labourer
11. | Combined water-proof and heat-insulation: | m2 | 1.53 | insulator | 0.0106 t | bitumen | 0.134 | 1.9757 | 1.5523 | 0
| 1 layer NEOACID sheet |  | 1.53 | labourer | 1.15 m2 | NEOACID sheet
| 1 sheet/layer glass-laminate bituminous felt |  |  |  | 1.15 m2 | glass-lamin. bit.felt
| 4 cm foamed plastic board |  |  |  | 1.03 m2 | 4 cm foamed plastic
| 1 sheet/layer vapour barrier foil |  |  |  | 1.03 m2 | foil
12. | Combined water-proof and heat-insulation: | m2 | 1.1 | insulator | 0.6 kg | light-stability enamel | 0.135 | 1.9757 | 1.5523 | 0
| 1 coat light-stability enamel |  | 0.75 | labourer | 1.15 m2 | plastic/rubber felt/foil
| 1 sheet/layer water proof foil |  |  |  | 1.15 m | bond tape
| 6 cm foamed plastic board |  |  |  | 0.6 kg | adhesive
| 1 sheet/layer vapour-barrier foil |  |  |  | 1.03 m2 | 6 cm foamed plastic
[5 empty] | 1.03 m2 | foil

## 19. formwork (hidden)
Formwork (formwork systems) | [11 empty] | rendszerzsaluk
Nr. | Activity | Unit | Labour |  |  | Item number | Prices |  |  | Tételszám | Tételszöveg
|  |  | Assembly | Dismantle | Skill
Time standard
|  |  | (hour) |  |  |  | Material price | Fee | Machinery cost
PERI system formwork (support included)
1. | Slab/floor shuttering | m2 | 0.27 | 0.07 | carpenter | 0.155 | [5 empty] | PREI födémzssalu
|  |  | 0.3 | 0.07 | labourer
2. | Wall shuttering | m2 | 0.4 | 0.1 | carpenter | 0.156 | [5 empty] | PERI falzsalu
|  |  | 0.48 | 0.12 | labourer
3. | Pier/column shuttering (rectangular) | m2 | 0.4 | 0.1 | carpenter | 0.157 | [5 empty] | PERI pillér és oszlopzsalu, négyszögletes
|  |  | 0.6 | 0.15 | labourer
4. | Pier/column shuttering (cylindric) | m2 | 0.5 | 0.12 | carpenter | 0.158 | [5 empty] | PERI oszlopzsalu kör keresztmetsze
|  |  | 0.7 | 0.18 | labourer
5. | Beam shuttering | m2 | 0.4 | 0.1 | carpenter | 0.159 | [5 empty] | PERI gerenda zsalu
|  |  | 0.45 | 0.1 | labourer
PERI-RINGER system formwork (support included)
6. | Wall shuttering, single sided | m2 | 0.17 | 0.06 | carpenter | 0.160 | [5 empty] | PERI falzsalu, egyoldali
|  |  | 0.2 | 0.08 | labourer
7. | Wall shuttering, double sided | m2 | 0.12 | 0.04 | carpenter | 0.161 | [5 empty] | PERI kétoldalú falzsalú
|  |  | 0.15 | 0.05 | labourer
8. | Slab/floor shuttering | m2 | 0.18 | 0.09 | carpenter | 0.162 | [5 empty] | PERI RINGER födémzsalu
|  |  | 0.2 | 0.1 | labourer
SZABOLCS system metal formwork (support included)
9. | Wall shuttering, assembled in-situ | m2 | 1.0 | 0.2 | carpenter | 0.163 | [5 empty] | falzsalu gelyszyíni szerelés
|  |  | 1.4 | 0.2 | labourer
10. | Wall shuttering, pre-assembled large panels | m2 | 0.4 | 0.1 | carpenter | 0.164 | [5 empty] | előre összeszerelt nagytáblás panelek
|  |  | 0.5 | 0.1 | labourer
DOKA system formwork (support included)
11. | Wall shuttering, double sided | m2 | 0.45 | 0.05 | shutt.fitter | 0.165 | [5 empty] | Doka kétoldali falzsalu
|  |  | 0.45 | 0.05
| SCAN-FORM rsystem formwork (support included) | [8 empty] | keretes falzsalu rendszer?
12. | Wall shuttering, single sided | m2 | 0.5 | 0.02 | carpenter | 0.166 | [5 empty] | egyoldali falzsalu
|  |  | 0.6 | 0.03 | labourer
13. | Wall shuttering, double sided | m2 | 0.7 | 0.04 | carpenter | 0.167 | [5 empty] | kétoldali falzsalu
|  |  | 0.9 | 0.06 | labourer
14. | Assembling supports/stands | lm | 0.04 | 0.04 | carpenter | 0.168 | [5 empty] | támasztólábak összeszerelése (födém és tető)
| for slab/roof shuttering |  | 0.05 | 0.06 | labourer
15. | Assembling slab/roof shuttering | m2 | 0.1 | 0.1 | carpenter | 0.169 | [5 empty] | gerenda vagy tetőssalu szerelése
|  |  | 0.14 | 0.17 | labourer
16. | LIFT-FORM construction system
| Assembling lift jack/post of 1.2 m | pair | 1.0 | 0.85 | smith | 0.170
| height (assembling off 2 parts each) |  | 1.0 | 0.85 | labourer
17. | Assembling space lattice structure | m2 | 0.95 | 0.85 | smith | 0.171 | [5 empty] | térrácsszerkezet összeszerelése
|  |  | 0.95 | 0.85 | labourer
18. | Load transfer to column or to wall | m2 | 0.8 | 0.5 | smith | 0.172 | [5 empty] | teherátadás falra vagy oszlopra
|  |  | 0.8 | 0.5 | labourer
19. | Assembling handrail | 10 lm | 0.65 | 0.45 | smith | 0.173 | [5 empty] | korlát bontása
|  |  | 0.65 | 0.45 | labourer
20. | lifting/elevation speed: 1.5 hour/1.2 m
dismantle speed: 1.4 hour/1.2 m

## 17. shuttering
Shuttering (auxiliary structures)
Nr. | Activity | Unit | Labour |  |  | Material |  |  | Item number | Prices
|  |  | Assembly | Dismantle | Skill | Quantity |  | Product
|  |  | Time standard |  |  | First built | Rebuilt
|  |  | (hour) | [6 empty] | Material price | Fee | Machinery cost | MEVA renting price
1. | Wall shuttering, double sided, | m2 | 0.47 | 0.13 | carpenter | 0.029 m3 | 0.0049 m3 | plank | 0.136 | 0.21504 | 12.973 | 0 | 7.056
| vertical or lean surface |  | 0.1 | 0.04 | labourer | 0.0143 m3 | 0.0014 m3 | lagging strip
2. | Wall shuttering, double sided, | m2 | 0.99 | 0.26 | carpenter | 0.0366 m3 | 0.0061 m3 | plank | 0.137 | 0.21504 | 20.5128 | 0 | 17.136
| bent surface |  | 0.24 | 0.07 | labourer | 0.0044 m3 | 0.0004 m3 | board
[6 empty] | 0.0018 m3 | 0.0002 m3 | log (bar)
3. | Wall shuttering, single sided, | m2 | 0.38 | 0.1 | carpenter | 0.0282 m3 | 0.0048 m3 | plank | 0.138 | 0.21504 | 17.7408 | 0 | 25.2
| vertical or lean surface |  | 0.09 | 0.02 | labourer | 0.0111 m3 | 0.0011 m3 | board
[6 empty] | 0.0193 m3 | 0.0015 m3 | log (bar)
[6 empty] | 0.0128 m3 | 0.0006 m3 | lumber
4. | Wall shuttering, single sided, | m2 | 0.95 | 0.2 | carpenter | 0.034 m3 | 0.0053 m3 | plank | 0.139 | 0.21504 | 27.0547 | 0 | 32.256
| bent surface |  | 0.24 | 0.05 | labourer | 0.044 m3 | 0.0033 m3 | log (bar)
[6 empty] | 0.0182 m3 | 0.0009 m3 | lumber
5. | Column shuttering, | m2 | 1.07 | 0.27 | carpenter | 0.042 m3 | 0.007 m3 | plank | 0.140 | 1.7338 | 15.3014 | 0 | 45.696
| rectangular, cylindric or polygonal |  | 0.25 | 0.07 | labourer | 0.0251 m3 | 0.0025 m3 | rib
6. | Column shuttering, | m2 | 0.83 | 0.22 | carpenter | 0.059 m3 | 0.0098 m3 | plank | 0.141 | 0.21504 | 52.1136 | 0 | 132.72
| non-uniform cross section |  | 0.21 | 0.06 | labourer | 0.027 m3 | 0.0027 m3 | rib
7. | Shuttering pier or sleeve foundation, | m2 | 0.64 | 0.16 | carpenter | 0.055 m3 | 0.0092 m3 | plank | 0.142 | 0.19824 | 10.201 | 0 | 92.4
| frustum (conic/pyramid) surface |  | 0.16 | 0.04 | labourer | 0.027 m3 | 0.0027 m3 | board
8. | Shuttering beams, ring-beams, | m2 | 1.3 | 0.38 | carpenter | 0.0515 m3 | 0.0086 m3 | plank | 0.143 | 0.21504 | 23.2848 | 0 | 21.84
| with support, below 6 m height |  | 0.32 | 0.09 | labourer | 0.0335 m3 | 0.0034 m3 | board
[6 empty] | 0.045 m3 | 0.003 m3 | log (bar)
[6 empty] | 0.0154 m3 | 0.008 m3 | lumber
9. | Shuttering beams, ring-beams, | m2 | 0.85 | 0.23 | carpenter | 0.046 m3 | 0.0078 m3 | plank | 0.144 | 0.21504 | 29.9376 | 0 | 28.56
| without support, above 6 m height |  | 0.21 | 0.06 | labourer | 0.0335 m3 | 0.0034 m3 | board
10. | Shuttering slab, with support, | m2 | 0.83 | 0.24 | carpenter | 0.04 m3 | 0.0066 m3 | plank | 0.145 | 0.21504 | 9.4248 | 0 | 7.56
| below 6 m height |  | 0.21 | 0.06 | labourer | 0.019 m3 | 0.002 m3 | board
[6 empty] | 0.026 m3 | 0.0026 m3 | log (bar)
[6 empty] | 0.012 m3 | 0.0012 m3 | lagging strip
11. | Shuttering slab, without support, | m2 | 0.38 | 0.11 | carpenter | 0.032 m3 | 0.0053 m3 | plank | 0.146 | 0.21504 | 12.7512 | 0 | 8.568
| above 6 m height |  | 0.09 | 0.03 | labourer | 0.019 m3 | 0.002 m3 | board
[6 empty] | 0.012 m3 | 0.0012 m3 | lagging strip
12. | Shuttering slab-and-girder, | m2 | 0.98 | 0.27 | carpenter | 0.045 m3 | 0.0075 m3 | plank | 0.147 | 0.21504 | 17.7408 | 0 | 19.824
| with support, below 6 m height |  | 0.24 | 0.07 | labourer | 0.0111 m3 | 0.0011 m3 | board
[6 empty] | 0.0311 m3 | 0.0031 m3 | log (bar)
13. | Shuttering slab-and-girder, | m2 | 0.63 | 0.17 | carpenter | 0.0335 m3 | 0.0056 m3 | plank | 0.148 | 0.21504 | 22.176 | 0 | 21.504
| without support, above 6 m height |  | 0.16 | 0.04 | labourer | 0.0101 m3 | 0.001 m3 | board
[6 empty] | 0.012 m3 | 0.0012 m3 | lagging strip
14. | Planing any plank (shuttering board) | m2 | 0.3 |  | carpenter | - | - | - | 0.152 | 0.84672 | 0.99792 | 0 | 0
15. | Planing edge for/at joints/bonds | m | 0.05 |  | carpenter | - | - | - | 0.153 | 0 | 3.9917 | 0 | 0
16. | Stair (flight) shuttering, with support, | m2 | 1.08 | 0.32 | carpenter | 0.066 m3 | 0.011 m3 | plank | 0.154 | 0.21504 | 14.6362 | 0 | 0
| below 6 m height |  | 0.36 | 0.08 | labourer | 0.008 m3 | 0.0008 m3 | board
[6 empty] | 0.0022 m3 | 0.00023 m3 | log (bar)

## 18. scaffolding
Scaffolding (auxiliary structures)
Nr. | Activity | Unit | Labour |  |  | Material |  |  | Item number | Prices
|  |  | Assembly | Dismantle | Skill | Quantity |  | Product
|  |  | Time standard |  |  | First built | Rebuilt
|  |  | (hour) | [6 empty] | Material price | Fee | Machinery cost
1. | External high-duty scaffolding, | m3 | 0.45 | 0.18 | carpenter | 0.058 m3 | 0.0039 m3 | log (bar) | 0.174 | 0.50064 | 6.3202 | 0
| below 20 m height, above 10 kN/m2 |  | 0.12 | 0.06 | labourer | 0.0162 m3 | 0.0005 m3 | board
| load-bearing capacity |  |  |  |  | 0.0047 m3 | 0.0003 m3 | lumber
2. | Access scaffolding, | m2 | 1.05 | 0.42 | carpenter | 0.17 m3 | 0.0113 m3 | log (bar) | 0.175 | 2.0429 | 11.1989 | 0
| at high-duty scaffolds |  | 0.5 | 0.26 | labourer | 0.0522 m3 | 0.0017 m3 | board
[6 empty] | 0.0065 m3 | 0.0002 m3 | plank
3. | Internal tubular scaffolding, | m2 | 0.73 | 0.48 | carpenter | 0.058 m3 | 0.001 m3 | board | 0.176 | 0.11136 | 22.176 | 0
| single storey, below 10 m height |  | 0.18 | 0.12 | labourer | 11.25 m | 0.1424 m3 | scaffold tube
4. | Internal tubular scaffolding, | m2 | 0.81 | 0.52 | carpenter | 0.067 m3 | 0,0011 m3 | boardx | 0.177 | 33.9125 | 25.5024 | 0
| multi-storey, above 10 m height |  | 0.22 | 0.15 | labourer | 16.2 m | 0.205 m | scaffold tube
5. | Internal scaffolding assembled | m2 | 0.12 | 0.05 | carpenter | 0.013 m3 | 0.0008 m3 | lumber | 0.178 | 0.29568 | 7.3181 | 0
| off access scaffold pieces (scales), |  | 0.16 | 0.12 | labourer | 2.45 m | 0.0612 m | scale (ladder)
| below 10 m height |  |  |  |  | 0.059 m3 | 0.001 m3 | board
6. | External tubular scaffolding, with | m2 | 0.27 | 0.16 | carpenter | 3.2 m3 | 0.04 m3 | scaffolding tube | 0.179 | 0.7728 | 4.657 | 0
| scales (ladders), 2 stands/posts, |  | 0.06 | 0.04 | labourer | 0.0135 m3 | 0.0002 m3 | board
| 2 boards, below 20 m height |  |  |  |  | 0.0023 m3 | 0.00023 m3 | plank
7. | External tubular scaffolding, with | m2 | 0.3 | 0.2 | carpenter | 3.3 m3 | 0.041 m3 | scaffolding tube | 0.180 | 0.73248 | 5.1005 | 0
| scales (ladders), 2 stands/posts, |  | 0.06 | 0.04 | labourer | 0.0135 m3 | 0.002 m3 | board
| 2 boards, above 20 m height |  |  |  |  | 0.23 m3 | 0.0001 m3 | plank
8. | Bracket scaffolding, single | m2 | 2.49 | 0.74 | carpenter | 0.055 m3 | 0.0019 m3 | log (bar) | 0.181 | 2.1336 | 1.2197 | 0
|  |  | 0.45 | 0.31 | labourer | 0.118 m3 | 0.002 m3 | board
[6 empty] | 0.032 m3 | 0.06 m3 | plank
9. | Assembling safety railing | lm | 0.36 | 0.09 | carpenter | 0.036 m3 | 0.002 m3 | log (bar) | 0.182 | 0.07392 | 1.3306 | 0
|  |  | 0.15 | 0.07 | labourer | 0.063 m3 | 0.002 m3 | plank
10. | Assembling stand/support for | lm | 2.03 | 0.81 | carpenter | 0.29 m3 | 0.02 m3 | log (bar) | 0.184 | 3.2894 | 29.9376 | 0
| RC beam shuttering, height range |  | 0.59 | 0.44 | labourer | 0.079 m3 | 0.0026 m3 | board
| of 6-10 m, below 20 kN/m2 |  |  |  |  | 0.0048 m3 | 0.0002 m3 | plank
load-bearing capacity
11. | Assembling stand/support for | m3 | 0.06 | 0.02 | carpenter | 0.046 m3 | 0.003 m3 | log (bar) | 0.185 | 3.8539 | 37.6992 | 0
| RC slab/floor shuttering (plain or |  | 0.08 | 0.05 | labourer | 0.0041 m3 | 0.0041 m3 | board
| slab-and-girder floor), below |  |  |  |  | 0.0008 m3 | 0.0001 m3 | lumber
10 m height, load-bearing
capacity range of 5-12 kN/m2
12. | Preparing working storey | m2 | 0.18 | 0.06 | carpenter | 0.067 m3 | 0.0011 m3 | board | 0.186 | 1.2902 | 2.2176 | 0
| (platform) of/on scaffolding, |  | 0.08 | 0.04 | labourer
single (laminate/layer) boarding

## 20. plastering
Plastering
Nr. | Activity | Unit | Labour |  | Materialx |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Wall plastering, internal, any surface, | m2 | 0.39 | mason | 0.016 m3 | internal lime-mortar | 0.188 | 4.116 | 7.644 | 0
| manually (std. thickness 1.5 cm) |  | 0.20 | labourer.
2. | Ceiling plastering, any surface, | m2 | 0.49 | mason | 0.004 m3 | internal lime-mortar | 0.189 | 5.0568 | 9.3912 | 0
| manually |  | 0.15 | carpenter | 0.013 m3 | improved internal lime-mortar
|  |  | 0.31 | labourer
3. | Wall rendering, internal, any surface, | m2 | 0.26 | mason | 0.016 m3 | internal lime-mortar | 0.190 | 10.3488 | 4.4352 | 0
| equipped |  | 0.12 | labourer
4. | Ceiling rendering, any surface, | m2 | 0.42 | mason | 0.004 m3 | internal lime-mortar | 0.191 | 12.2304 | 5.2416 | 0
| equipped |  | 0.18 | labourer | 0.013 m3 | improved internal lime-mortar
5. | Water-proof wall plastering, at industrial | m2 | 1.29 | mason | 0.018 m3 | water-proof cement-mortar | 0.192 | 22.5658 | 6.431 | 0
| buildings, thickness: 3x5 mm (3 coats) |  | 0.29 | labourer
6. | External plastering, manually | m2 | 0.58 | mason | 0.02 m3 | external improved lime-mortar | 0.193 | 6.2328 | 11.5752 | 0
| (lime-mortar rendering, stone-dust |  | 0.53 | labourer | 0.0075 m3 | surfacing mortar
mortar floating/covering)
7. | External plastering, equipped rendering | m2 | 0.5 | mason | 0.02 m3 | external improved lime-mortar | 0.194 | 11.4912 | 14.0448 | 0
|  |  | 0.22 | labourer | 0.0075 m3 | surfacing mortar
8. | Scouring, terracotta (brick) surface | m2 | 0.16 | mason | 0.0055 m3 | external improved lime-mortar | 0.195 | 1.2768 | 1.9152 | 0
| (lime- or cement-mortar) |  | 0.12 | labourer | 0.0055 m3 | or cement-mortar floating

## 21. tiling and covering
Tiling and covering
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material | Fee | Machinery cost
1. | Subconcrete | m3 | 7.54 | labourer | 1.01 m3 | concrete | 0.197 | 89.376 | 38.304 | 0
(screeded and floated)
2. | Concrete flooring | m2 | 0.32 | mason | 0.021 m3 | cement-mortarx | 0.198 | 16.2288 | 6.9552 | 0
| on existing base, |  | 0.26 | labourer
cement-mortar (2 cm)
3 | Tiling | m2 | 1.11 | tiler | 25.5 pcs | mosaic tile (20x20 cm) | 0.199 | 28.6944 | 12.2976 | 0
| (floor, wall, column, pier, etc.) |  | 1.11 | labourer | 0.026 m3 | and cement-mortarx
[5 empty] | or 102 pcs | or 10x10 cm delftware tile |  | 45.911 | 19.6762 | 0
[5 empty] | and 0.0155 m3 | and cement-mortarx
[5 empty] | or 46 pcs | or 15x15 cm tile and |  | 63.1277 | 27.0547 | 0
[5 empty] | and 0.016 m3 | improved lime-stone mortarx
4. | Covering footings, | m2 | 0.15 | tiler | 0.21 m2 | mosaic tile (20x20 cm) or | 0.200 | 23.52 | 10.08 | 0
| (internal or external) |  | 0.15 | labourer | 10.2 pcs | 10x10 cm delftware tiling |  | 35.28 | 15.12 | 0
| single row, straight |  |  |  | 6.8 pcs | or 15x15 cm tile |  | 32.2224 | 13.8096 | 0
5. | Wooden wall-covering | m2 | 0.7 | carpenter | 1.1 m2 | wood panel (e.g. wainscot) | 0.201 | 8.232 | 3.528 | 0
6. | Parquetry, | m2 | 0.28 | carpenter | 0.72 m2 | board (18 or 24 mm) | 0.202 | 31.752 | 13.608 | 0
| (subflooring, pinning, sanding, |  | 0.3 | floor layer (seamless) | 0.005 m3 | rabbet
| enamelling included) |  | 0.1 | labourer | 0.95 m2 | parquetry
[5 empty] | 0.08 m2 | wood rib
[5 empty] | 0.25 kg | enamel
[5 empty] | 0.15 m | sandpaper, 40 cm width
7. | Parquetry, | m2 | 0.6 | floor layer (seamless) | 0.95 m2 | parquetry | 0.203 | 43.512 | 18.648 | 0
| (bonding, sanding, |  | 0.1 | labourer | 0.08 m2 | wood rib
| enamelling included) |  |  |  | 2 kg | "bonobit s"
[5 empty] | 4 kg | "ÉKIN 149"
[5 empty] | 0.25 kg | enamel
[5 empty] | 0.15 m | sandpaper, 40 cm width
8. | Parquetry, mosaic, | m2 | 0.35 | floor layer (seamless) | 1.01 m2 | mosaic parquetry | 0.204 | 37.632 | 16.128 | 0
| (bonding, sanding, |  |  |  | 1.7 kg | disperse bond
| enamelling included) |  |  |  | 0.25 kg | enamel
[5 empty] | 0.15 m | sandpaper, 40 cm width
9. | Rolled plastic sheet (PVC) | m2 | 0.26 | tiler | 1.05 m2 | PVC sheet | 0.205 | 18.3456 | 7.8624 | 0
| flooring, bonded |  |  |  | 0.6 kg | bond
10. | Fitted carpet, on existing | m2 | 0.3 | tiler | 1.1 m2 | carpet | 0.206 | 23.52 | 10.08
| base, bonded |  |  |  | 0.8 kg | "Palmafix" bond
11. | Magnesite (composition) | m2 | 0.31 | tiler | 11.6 kg | magnesite | 0.207 | 17.8752 | 7.6608 | 0
| flooring (any color) |  | 0.31 | labourer | 9.5 kg | magnesium-chloride flake
12. | Basalt chip wear concrete | m2 | 0.25 | labourer | 1.02 m2 | basalt chip- | 0.208 | 2.399 | 0.33264 | 0
| flooring, thickness 3 cm |  |  |  |  | wear concretex
13. | Levelling course, varying | m3 | 7.5 | labourer | 1.01 m3 | mortarx | 0.209 | 5.3155 | 6.2093 | 0
thickness, on existing base,
mortar or concrete spreading

## 22. tinsmith
Tinsmith works
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Installing downpipes, eaves, | m | 0.35 | tinsmith | 1.01 m | elements as specified | 0.210 | 43.512 | 18.648 | 0
| gutter spouts |  | 0.38 | labourer |  | (downpipes, eaves, etc.)
2. | Flashing eaves, walls, chimney | m | 0.29 | tinsmith | 1.03 m | elements as specified | 0.211 | 18.3456 | 7.8624 | 0
| stacks, expansion joints, hood |  | 0.30 | labourer |  | (cornice, wall flashings, etc.)
moulds, string cornices, valleys
3. | Other tinsmith structures/works | pcs | 0.10 | tinsmith | 1 pc | elements as specified | 0.212 | 29.4 | 12.6 | 0
| (dormer window, skylight, etc.) |  | 0.10 | labourer |  | (window, roof exit, etc.)

## 23. glazing
Glazing
Nr. | Activity |  | Unit | Labour |  |  | Material |  | Item number | Prices
|  |  |  | Single | Double | Skill | Quantity | Product
|  |  |  | glazing | glazing
|  |  |  | Time standard (hour) | [5 empty] | Material price | Fee | Machinery cost
1. | Glazing (sheet glass) |  | m2 | 0.3 | 0.55 | glazier | 1.03 m2 | sheet glass | 0.213 | 10.8192 | 4.6368 | 0
2. | Cast glass |  | m2 | 0.31 | 0.64 | glazier | 1.03 m2 | cast glass | 0.214 | 36.456 | 15.624 | 0
(decorative glass, wired glass)
3. | Heat-insulating glass |  | m2 | 0.95 | 1.24 | glazier | 1.02 m2 | laminated glass | 0.215 | 36.456 | 15.624 | 0
(compound)
4. | Drawn glass | plain | m2 | 0.62 |  | glazier | 1.08 m2 | profiled glass | 0.216 | 72.912 | 31.248 | 0
5. | profiles | compound | m2 | 0.91 |  | glazier | 2.04 m2 | profiled glass | 0.217 | 38.808 | 16.632 | 0

## 24. joinery and carpentry
Joinery and carpentry works
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material price | Fee | Machinery cost
1. | Placing door, window, gate, battening | pcs | 0.7 | mason | 1 pc | elements as specified | 0.218 | 348.096 | 145.152 | 0
| (inwalled during masonry works) |  | 0.7 | labourer |  | (door, window, etc.)
2. | Placing door, window, gate, battening | pcs | 1.16 | mason | 1 pc | elements as specified | 0.219 | 338.688 | 145.152 | 0
| (after masonry works, subsequently) |  | 1.16 | labourer |  | (door, window, etc.)

## 25. fitting smith
Fitting-smith structures
Nr. | Activity |  | Unit | Labour |  | Material |  | Item number | Prices
|  |  |  | Time standard | Skill | Quantity | Product
|  |  |  | (hour) |  |  |  |  | Material cost | Fee | Machinery cost
1. | Placing steel door or window, | subsequent | pcs | 1.12 | mason | 1 pc | elements as specified | 0.220 | 482.16 | 206.64 | 0
| perimeter below 5 m |  |  | 1.12 | labourer |  | (door, window, etc.)
|  | masonry | pcs | 0.5 | mason
|  | included |  | 0.5 | labourer
2. | Placing steel portal, | subsequent | pcs | 1.33 | mason | 1 pc | elements as specified | 0.221 | 1176 | 504 | 0
| door or window, |  |  | 1.33 | labourer |  | (door, window, etc.)
perimeter above 5 m,
| (operating devices included) | masonry | pcs | 0.6 | mason
|  | included |  | 0.6 | labourer
3. | Placing handrail or scale, |  | kg | 0.32 | mason | 1.0 lm | elements as specified | 0.222 | 4.2336 | 1.8144 | 0
| pocket or anchor bolt fixing |  |  | 0.32 | labourer |  | (handrail, scale, etc.)
4. | Placing structural steel elements |  | t | 34.0 | smith | as specified |  | 0.223 | 2352 | 1008 | 0
| (e.g. steel-frame pieces) |  |  | 17.0 | labourer

## 26. dec and coating
Decoration and coating
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material cost | Fee | Machinery cost
1. | Limewash, manual | m2 | 5.96 | painter | 0.039 m3 | caustic limex | 0.224 | 1.2768 | 1.9152 | 0
| (3 coats) |  | 1.98 | labourer | 1.9 kg | gypsum
2. | Limewash, equipped | m2 | 4.72 | painter | 0.039 m3 | caustic limex | 0.225 | 4.032 | 6.048 | 0
| (3 coats) |  | 1.58 | labourer | 1.9 kg | gypsum
3. | Internal (distemper) paint, | m2 | 8.74 | painter | 0.02 m3 | caustic limex | 0.226 | 1.47 | 2.73 | 0
| manual |  | 2.91 | labourer | 21.0 kg | Vienna white
[5 empty] | 2.0 kg | gypsum
4. | Exterior face decoration, | m2 | 10.98 | painter | 90 kg | Vliesin | 0.227 | 28.224 | 12.096 | 0
| manual (e.g. Vliesinnel) |  | 3.67 | labourer | 3 kg | Vliesin-Fixative
5. | Exterior face decoration | m2 | 9.2 | painter | 90 kg | Vliesin | 0.228 | 6.8208 | 2.9232 | 0
| (painting), equipped |  | 3.0 | labourer | 3 kg | Vliesin-Fixative
6. | Surface preparation | m2 | 7.2 | painter | 3.6 kg | gypsum | 0.229 | 1.2096 | 1.4784 | 0
| (stopping, sanding, dusting) |  | 2.3 | labourer | 0.0045 m3 | caustic limex
7. | Decoration and tapestry | m2 | 24.0 | paper-hanger | 114 m2 | wallpaper | 0.230 | 9.1728 | 3.9312 | 0
(wallpapering)
8. | Unrusting on surface | m2 | 7.12 | painter | 7 kg | cleaner's naphta | 0.231 | 0.20832 | 1.4414 | 0
9. | Unrusting on pipes, | m | 3.52 | painter | 2 kg | cleaner's naphta | 0.232 | 2.688 | 1.008 | 0
diameter below 3"
10. | Priming (paint) on surface | m2 | 10.96 | painter | 11 kg | priming paint | 0.233 | 2.8224 | 1.2096 | 0
11. | Priming (paint) on pipes, | m | 3.45 | painter | 4 kg | priming paint | 0.234 | 0.17472 | 0.88704 | 0
diameter below 3"
12. | Covering paint on surface, | m2 | 21.0 | painter | 11 kg | covering paint | 0.235 | 5.6448 | 2.7216 | 0
2 coats,
13. | Covering paint on pipes, | m | 5.8 | painter | 5 kg | covering paint | 0.236 | 0.8736 | 3.4944 | 0
diameter below 3", 2 coats
14. | Enamel paint on surface | m2 | 14.53 | painter | 13 kg | enamel paint | 0.237 | 10.08 | 15.12 | 0
15. | Enamel paint, on pipes, | m | 3.45 | painter | 3 kg | enamel paint | 0.238 | 0.8736 | 3.4944 | 0
diameter below 3"

## 27. building service
Building service conduits
Nr. | Activity | Unit | Labour |  | Material |  | Item number | Prices
|  |  | Time standard | Skill | Quantity | Product
|  |  | (hour) |  |  |  |  | Material cost | Fee | Machinery cost
1. | Installing water-pipe, in chase or in duct, | lm | 0.46 | plumber | 1.03 m | galvanized pipe | 0.239 | 6.6528 | 8.1312 | 0
| diameter below 2" |  | 0.46 | labourer
2. | Installing gas-pipe, out of wall or in chase, | lm | 0.58 | plumber | 1.04 m | (black) gaspipe | 0.240 | 30.576 | 13.104 | 0
| weld joints, tested, diameter below 2" |  | 0.58 | labourer | 0.5 pcs | (gas)pipe bracket
3. | Installing PVC drainage pipe, in chase | lm | 0.59 | plumber | 0.85 m | PVC drainage pipe | 0.241 | 3.4339 | 0.66528 | 0
| or in duct, diameter below 110 mm |  | 0.59 | labourer | 0.5 pcs | PVC bent pipe