## Sample
Tasks | Start date | Days to complete | Tasks | Subtasks | Days to complete
Task 1 | 24. April | 3 | Substructure
Task 2 | 29. April | 7 |  | Excavation | 4
Task 3 | 7. May | 11 |  | Foundations | 12
Task 4 | 21. May | 5 |  | Insulations | 4
Task 5 | 27. May | 8 |  | Basement walls | 8
Task 6 | 5. June | 4 | Superstructure
Task 7 | 11. June | 8 |  | Ground floor slab | 4
Task 8 | 20. June | 6 |  | Ground floor walls | 13
|  |  |  | First floor slab | 4
|  |  |  | Attic construction | 10
Finishing works
|  |  |  | Insulations | 8
|  |  |  | Roof tiling works | 3
|  |  |  | Floor and wall laying | 6
|  |  |  | Painting | 8
|  |  |  | Joinery work | 3
[5 empty] | 87 | sum