## Slide 1: Project management Pmo – the basics
Éva Németh
Nóra Kollárik

## Slide 2: History of PMO
1910

## Slide 3: History of PMO
1910
1950s

## Slide 4: History of PMO
1910
1950s
1980s

## Slide 5: History of PMO
1910
1950s
1980s
1990s

## Slide 6: History of PMO
1910
PMO
1950s
1980s
1990s
PMO
PMO
PMO

## Slide 7: Definition of pmo
A group or department that defines and maintains project management standards across an organization.
The keeper of documentation, guidance, and metrics for project execution, ensuring projects are completed on time and within budget.
Can also have certain privileges over projects that the PM is not entitled to (e.g. making business/strategic decisions to put on hold or stop a project completely)

## Slide 8: Who needs a pmo?
Projects are not properly aligned with business goals/do not deliver business value
You may need a PMO if:
Projects finish later than planned or over budget
Stakeholders do not have visibility into project progress
No standardized process for initiating and executing projects
Project success cannot be tracked accurately
Skills and resources across projects and programmes are not efficiently used

## Slide 9: levels of Pmo
Directive PMO
Takes over the management of the project by providing experience and resources. This requires high maturity PMOs, usually professional project managers.
Has a high degree of control in projects.
Supportive PMO
Supplies guidelines, templates, best practice, training, some status reporting.
Has no or very little influence and control over projects.
Controlling PMO
Requires compliance to organizational tools, processes, and standards applied. In case of non-compliance, initiates and enforces corrective actions.
Has a moderate degree of control in projects.
PMOs operate according to the organization’s needs and goals, so each PMO is structured differently
Weak matrix
Balanced matrix
Strong matrix

## Slide 10: PMO maturity
Absent

## Slide 11: PMO maturity
Initial
Absent

## Slide 12: PMO maturity
Initial
Established
Absent

## Slide 13: PMO maturity
Initial
Established
Grown up
Absent

## Slide 14: PMO maturity
Initial
Established
Grown up
Mature
Absent

## Slide 15: PMO maturity
Initial
Established
Grown up
Mature
Best in class
Absent

## Slide 16: T&T PROJECT Organization sample – Mirrored Project Organization
PMO
Cross Functions
T&T Program Management
PMO
Cross Functions
Work- stream A
Work- stream B
Work- stream X
Program Management
Work- stream A
Work- stream B
Work- stream X
Project Steering Committee
Executive Steering Committee
  Responsible for all PM related topics and interfacing with the organization on general requirements (planning, reporting, etc.).
  Responsible for supporting of PM related topics and interfacing with Customer PMO on general requirements (planning, reporting, etc.).
  Responsible for administration and content of project EPM and customer EPM (Enterprise Project Management tool).
Project Management Office
Customer
T-Systems

## Slide 17: Pmo key tasks
Reporting
Cost management
Support
Project management
Project information
Resource management
Communication

## Slide 18: PMO tasks – initiation & planning 1/3
CONSULTANCY
COMMUNICATION MAPPING
GENERAL – REPORTING & TRACKING
 | Description | 
 | Managing Resourcing Forecast Report ReM Tool entries for new & closing assignments Organizing Resourcing Reviews Time & Cost Tracking Collecting source data for Project Reporting Updating Risks & Issues & Action Items Log | 
 | Project Organization Chart Building out Communication Channels Collecting source data for Project Reporting Updating Risks & Issues & Action Items Log Meeting Minutes Monitoring Changes & updating Project Data Project Portfolio – central storage | 
 | All additionals to be requested by the Stream Lead Creating an overview of project specific processes, if necessary - MS Visio | 
Notes: 13.08.2007
18
Autor / Thema der Präsentation

## Slide 19: PMO Tool-KIT 2/3
GENERAL – TOOL KIT
 | Description | 
 | New Joiner Form & Kickstart 4 onboarding Resource Management Tool SharePoint Portal (central documental repository) SharePoint Portal (project-specific site) Project Knowledge Center Expense Tracking Tool Accounting System (optionally requested for PMOs) Customer Project Reporting Tool Miles+ (time-writing tool) | 
 | Defining cross-functions & dependencies | 
 | MS applications – be an expert | 
 | Your unique soft-skills | 
Notes: 13.08.2007
19
Autor / Thema der Präsentation

## Slide 20: PMO roles & Tasks – on wide-scale 3/3

## Slide 21: Resource management tool
Derives from Competence DB
1. PM initiates request
  2. ReM Team accepts
    3. Seek for suitable candidate
      4. Capacity is OK
      5. Candidate approved by PM

## Slide 22: Resource forecast report

## Slide 23: Resource forecast report

## Slide 24: Communication register – simple

## Slide 25: Communication calendar

## Slide 26: Risk/issue log & action item list

## Slide 27: PMO’s Reporting basics
Red
Critical issues could not be solved.
Management review and decisions are necessary, the impact on business case and/or contractual milestone is likely or visible already. (e.g. agree on new budgets).
Might require management review.
Critical issues are identified or not yet solved. If issues are not solved within reasonable timeframe they will impact the business case and/or the deliverables.
Amber
No extra attention and action required.
All critical issues are under control. Business case and deliverables are on track. Customer is satisfied with T-Systems overall.
Green
Always applicable: If project status or one of the reported KPIs (time, budget, quality) is not green, back to green measures need to be set up as soon as possible.

## Slide 28: PMO success factors
The role of the PMO must be clearly defined
commitment of executive management is crucial
The PMO will only improve project performance if usage of proper processes and techniques are encouraged
Not mature enough?
Focus on Quick-wins
Pmp certification for mature PMO members
Learn how to walk before you try to run