## Slide 1: IT SERVICES HUNGARY PROJECT MANAGEMENT 2
Notes: Welcome
1st time ->introduction (subject, company)
Background info
ISTH supports the University
What is this subject about?
Have you ever hearder about PM or project?
What is the goal of this subject?
We’d like to teach practical things (PM1- with some basics, PM2 practical tasks)

## Slide 2
PROJECT MANAGEMENT 2 – TANTÁRGYI TEMATIKA

## Slide 3
PROJECT MANAGEMENT 2 – details & Requirements
  Subject name: Project management 2
  Frequency: 2 lessons per week
  Credit value: 3
  Date of subject: Academic year 2018-2019, Spring semester
  Type of subject: Compulsory
  Faculty: Engineering and Information Technology, University of Pécs, ITSH Office
  Subject responsible: Tibor Varga
  Mandatory requirements:
    Participation in lectures (2 absenteeism is allowed without official excuse)
    2 submit papers during the semester
    Higher than 50% success rate on the exam
    (each grade has to be higher that 50%)
  Course Requirement: Exam (written)
  Lecture notes: presenter’s slide deck and exercises

## Slide 4
PROJECT MANAGEMENT 2 – Agenda

## Slide 5: project process groups
Processes (47), process groups (5), knowledge areas (10)
Source: PMBOK Guide
 | Initiating | Planning | Executing | Controlling | Closing
Integration | Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Work | Monitor and Control Project Work Perform Integrated Change Control | Close Project or Phase
Scope |  | Plan Scope Management Collect Requirements Define Scope Create WBS |  | Validate Scope Control Scope | 
Time |  | Plan Schedule Management Define Activities Sequence Activities Estimate Activity Resources Estimate Activity Durations Develop Schedule |  | Control Schedule | 
Cost |  | Plan Cost Management Estimate Costs Determine Budget |  | Control Costs | 
Quality |  | Plan Quality Management | Perform Quality Assurance | Control Quality | 
HR |  | Plan Human Resource Management | Acquire Project Team Develop Project Team Manage Project Team |  | 
Comm. |  | Plan Communications Management | Manage Communications | Control Communications | 
Risk |  | Plan Risk Management Identify Risks Perform Qualitative Risk Analysis Perform Quantitative Risk Analysis Plan Risk Responses |  | Control Risks | 
Proc. |  | Plan Procurement Management | Conduct Procurements | Control Procurements | Close Procurements
Stakeholder | Identify Stakeholders | Plan Stakeholder Management | Manage Stakeholder Engagement | Control Stakeholder Engagement | 

## Slide 6: Process groups
Planning processes
Executing processes
Initiating processes
Closing processes
Enter Phase / Start project
Exit Phase / End project
Monitoring & Controlling processes

## Slide 7: INITIATION
Timing
Roles
Stakeholders
Deliverables
Effects
Quality requirements of the result
Project Sponsor, Project manager
Project Charter
MAIN INFORMATION, HIGH LEVEL PLANS
1. Initiation
2. Planning
3. Execution
4. Closing

## Slide 8: Initiation PROJECT CHARTER
Project master data
Project classification
Business case/need
High level project scope/out of scope, project deliverables, project success criteria
Project constraints and assumptions
Project budget (rough estimates)
Schedule (high level)
Main stakeholders (team members, contractors, pre-assigned resources’ with roles, etc.)
High-level project requirements
High-level project risks
DEFINING THE SCOPE, SCHEDULE, REQUIREMENTS

## Slide 9: KICK OFF MEETING
Project Charter
REM, Risk register
Organization chart
Schedule
Budget
Communication plan

## Slide 10: PLANNING
Schedule
Deliverables
Resource
Budget
Risks
Project manager, core project team
Detailed project plan, budget
DETAILED PLANS
1. Initiation
2. Planning
3. Execution
4. Closing

## Slide 11: KICK OFF MEETING REM, Risk register
Low | Medium | High
Low | Medium | Medium
Low | Low | Low
Probability
Impact (Q, C, T)

## Slide 12: KICK OFF MEETING ORGANIZATION CHART
MATRIX ORGANIZATIONAL STRUCTURE
PROJECT ORGANIZATION
ESCALATION PATH

## Slide 13: KICK OFF MEETING SCHEDULE
Planning, team setup
Project Setup
Activities
Kick off
2013.09.30.
2013.11.22.
Workshops
Execution
Approval
Approved T&T NS Process
Project closing
Closing
Project is closed
2013.12.20.
2013
September
October
November
December
Adoption
Process development
QG rollout
Rollout
DEFINING MAIN MILESTONES
PLANNING DEADLINES
Notes: Mire jó:
Pontosan látszik, hogy követik egymást az egyes taskok
Milyen logikai kapcsolat van a taskok között
A mérföldkövek segítségével ellenőrizni tudjuk a P előrehaladását, és ezeket riportáljuk a managementnek
Megmutatni e timeplant

## Slide 14
Notes: P org chart

## Slide 15: KICK OFF MEETING Communication plan
What | When | From whom | To whom
Status report | Biweekly | Program manager | Program SC members
SC call | Monthly | Program manager | Program SC members
Escalation | As needed | Program manager | Program SC members
PM call | Biweekly | Program manager | Program manager
Project status documents | Weekly | Program manager | Program manager
IDENTIFYING TARGET AUDIENCE
IDENTIFING COMMUNICATION TOOLS
PLANNING COMMUNICATION CHANNELS
Notes: Megmutatni az communicaton plant a (next slide)

## Slide 16: KICK OFF MEETING BUDGET
EXPENSES
CAPEX
OPEX
OPEX WH
External OPEX
RESOURCE ALLOCATION
DETAILED BUDGET ON AN AGREED LEVEL

## Slide 17: EXECUTIng/Controlling
Execute project plan
Validate Scope
Project change management
Risk management
Communication
Stakeholder management
Control Schedule
Project manager, project team, Sponsor, Stakeholders
Status reports
1. Initiation
2. Planning
3. Execution
4. Closing

## Slide 18: CLOSING
Customer acceptance
Financial closing
Lessons learned
Release resources
Project manager
Project Final Report
1. Initiation
2. Planning
3. Execution
4. Closing
Notes: Hol is tartunk ilyenkor?
A P mostanra már leszállította az összes leszállítandóját, de ez még nem azt jelenti, hogy a P teljes.
Hogyan is zárjunk le egy projektet?
Sokan azt gondolnák, hogy ez nem is olyan fontos része a pmnek. A P zárása azonban pont olyan fontos és hangsúlyos, mint a P összes többi fázisa az életciklusa során.
Nézzük milyen főbb lépési vannak a P zárásnak.
Az első és nélkülözhetetlen dokumentum, az Ügyfél formális elfogadó nyilatkozata, miért fontos ez?
(gondoljunk csak bele, lezárjuk e nélkül a P-et, és ha később az ügyfél azt mondja, hogy mégsem azt kapta amiben megállapodtunk, ezt/azt még javítsunk rajta, akkor mit csinálunk? újra össze kell szedni a team-et, plus ktg, stb..)
Pénzügyi zárás, teljeítési igazolások kiállítása, számlák kifizetése, WBS kódok zárása
Beszállítói, alvállalkozói szerződések lezárása
LL megosztása, dokumentálása
Projekt dokumentumok archiválása
Erősforrások felszabadítása
Az első lépés azonban a Projektzáró jelentés elkészítése és annak bemutatása a sponsor felé.
A projektzáró jelentés célja az elvégzett tevékenységek és a projekt végrehajtása során szerzett tapasztalatok összefoglalása, bemutatása.